## Gantt
STT | Phase | Module | Task | Mo ta chi tiet | Start Date | End Date | 27-04 | 28-04 | 29-04 | 30-04 | 01-05 | 02-05 | 04-05 | 05-05 | 06-05 | 07-05 | 08-05 | 09-05 | 11-05 | 12-05 | 13-05 | 14-05 | 15-05 | 16-05 | 18-05 | 19-05 | 20-05 | 21-05 | 22-05
1 | Implementation | Auth | Auth-BE-01: Entity & Migration | Dinh nghia User, Role, Permission va chay migration PostgreSQL. | 01/05 | 01/05
2 | Implementation | Auth | Auth-BE-02: Register & Login Logic | Service bcrypt password, phat hanh Access/Refresh JWT. | 02/05 | 02/05
3 | Implementation | Auth | Auth-BE-03: Logout & Token Rotation | Thu hoi refresh token trong Redis khi logout/compromised token. | 02/05 | 02/05
4 | Implementation | Auth | Auth-FE-04: Register/Login Screens | UI form voi React Hook Form + Zod validation. | 02/05 | 03/05
5 | Implementation | Auth | Auth-FE-05: Auth Store & Interceptor | Axios interceptor tu dong attach token va handle 401. | 03/05 | 03/05
6 | Implementation | Auth | Auth-BE-06: RBAC Guards | Decorator + Guard phan quyen Admin/Teacher/Student. | 04/05 | 04/05
7 | Implementation | Classroom | Class-BE-01: CRUD Class APIs | API tao/cap nhat/lis class va quan ly danh sach thanh vien. | 04/05 | 04/05
8 | Implementation | Classroom | Class-BE-02: Enrollment Logic | Join class, approve/reject enrollment boi teacher. | 05/05 | 05/05
9 | Implementation | Classroom | Class-FE-03: Classroom Dashboard | UI danh sach lop theo vai tro teacher/student. | 05/05 | 06/05
10 | Implementation | Classroom | Class-FE-04: Member Management UI | UI quan ly thanh vien va trang thai enrollment. | 06/05 | 06/05
11 | Implementation | Problem | Prob-BE-01: Problem CRUD API | CRUD de bai, constraints, time/memory limit. | 05/05 | 05/05
12 | Implementation | Problem | Prob-BE-02: Testcase Management | Quan ly testcase public/hidden va metadata. | 06/05 | 06/05
13 | Implementation | Problem | Prob-FE-03: Problem Creator UI | UI tao/sua de bai va markdown statement. | 06/05 | 07/05
14 | Implementation | Problem | Prob-FE-04: Testcase UI Editor | Nhap testcase truc tiep hoac upload txt/zip. | 07/05 | 07/05
15 | Implementation | Submission | Sub-BE-01: Submission API | Nhan source code + language, tao submission record. | 07/05 | 07/05
16 | Implementation | Submission | Sub-BE-02: MinIO Integration | Luu source/artifact vao MinIO theo object key convention. | 07/05 | 08/05
17 | Implementation | Submission | Sub-FE-03: Code Editor Workspace | Monaco editor, language picker, submit action. | 08/05 | 08/05
18 | Implementation | Submission | Sub-FE-04: History & Verdict UI | UI lich su nop bai va ket qua testcase. | 08/05 | 09/05
19 | Implementation | Judge Core | Judge-BE-01: Redis Queue Producer | Day submission job vao queue theo priority. | 08/05 | 08/05
20 | Implementation | Judge Core | Judge-WK-02: Worker Consumer | Worker consume job, tai source tu storage, chuan bi run. | 09/05 | 09/05
21 | Implementation | Judge Core | Judge-WK-03: Result Persister | Tong hop verdict/runtime/memory va cap nhat DB. | 10/05 | 10/05
22 | Implementation | Sandbox | Sand-WK-01: Docker Driver | Adapter cho Docker create/start/stop/remove. | 09/05 | 10/05
23 | Implementation | Sandbox | Sand-WK-02: Resource & Security | cgroups + seccomp + network restriction. | 11/05 | 11/05
24 | Implementation | Sandbox | Sand-WK-03: Execution Scripts | Scripts compile/run va capture stdout/stderr. | 11/05 | 12/05
25 | Implementation | AI Integration | AI-BE-01: AI Service Client | Tich hop SDK AI + retry/backoff khi loi. | 11/05 | 11/05
26 | Implementation | AI Integration | AI-BE-02: Prompt Builder | Xay prompt theo de bai + submission context. | 11/05 | 12/05
27 | Implementation | AI Integration | AI-FE-03: AI Feedback UI | UI hien goi y AI va vi tri loi trong code. | 12/05 | 12/05
28 | Implementation | Realtime | WS-BE-01: Socket.io Gateway | WebSocket gateway va JWT handshake auth. | 12/05 | 12/05
29 | Implementation | Realtime | WS-BE-02: Event Emitter | Push trang thai Dang cham/Hoan thanh den dung user room. | 12/05 | 13/05
30 | Implementation | Realtime | WS-FE-03: Realtime Listener | FE listener cap nhat status/verdict khong reload. | 13/05 | 13/05
31 | Implementation | Storage | Storage-BE-01: Presign Upload/Download APIs | Hoan thien /storage/presign/upload va /storage/presign/download. | 13/05 | 13/05
32 | Implementation | Storage | Storage-BE-02: Bind Object Key API | Bind object key vao ai job/export/golden-solution. | 13/05 | 14/05
33 | Implementation | Storage | Storage-FE-03: Upload Test Route | Route /test upload image/file/zip/folder va hien thi logs. | 14/05 | 14/05
34 | Implementation | Observability | Obs-BE-01: Structured Logging | Them correlation id, log context cho API/worker. | 14/05 | 14/05
35 | Implementation | Observability | Obs-BE-02: Healthcheck & Readiness | Endpoints health/ready cho core-api va worker. | 15/05 | 15/05
36 | Implementation | DevOps | Ops-01: Docker Compose Hardening | Dong bo env, service dependency, startup order. | 15/05 | 15/05
37 | Testing | Unit Test | UT-01: Auth & Classroom | Test logic validation/business rules cua Auth/Classroom. | 13/05 | 14/05
38 | Testing | Unit Test | UT-02: Judge Logic & Mapping | Test map ket qua Docker sang AC/WA/TLE/RE. | 14/05 | 14/05
39 | Testing | Integration | IT-01: API End-to-End | Luong nop bai -> luu file -> queue -> nhan ket qua. | 15/05 | 15/05
40 | Testing | Integration | IT-02: Realtime Flow | Do tre va tinh chinh xac thong bao qua websocket. | 16/05 | 16/05
41 | Testing | Sandbox Test | ST-01: Security Escape | Gia lap tan cong escape container/fork bomb/system file. | 18/05 | 18/05
42 | Testing | Sandbox Test | ST-02: Resource Restriction | Test time/memory limits voi workload nang/loop vo han. | 18/05 | 18/05
43 | Testing | Frontend Test | FT-01: E2E User Flow | Playwright/Cypress login -> join class -> submit -> view verdict. | 19/05 | 20/05
44 | Testing | Frontend Test | FT-02: Cross-browser & Mobile | Kiem tra UI tren Chrome/Firefox/Safari + responsive. | 20/05 | 20/05
45 | Testing | AI Quality | AIT-01: Prompt Accuracy | Danh gia do huu ich AI tren bo testcase loi pho bien. | 19/05 | 19/05
46 | Testing | AI Quality | AIT-02: AI Latency Test | Kiem tra do tre AI va UX khi AI phan hoi cham. | 19/05 | 19/05
47 | Testing | Performance | PT-01: Load Testing | JMeter/Locust 100 concurrent submissions. | 21/05 | 21/05
48 | Testing | Storage Test | STO-01: Presign Expiration & Access | Test URL het han, object key sai, unauthorized access. | 21/05 | 21/05
49 | Testing | Storage Test | STO-02: Upload Type Matrix | Verify image/file/zip/folder upload va download. | 21/05 | 21/05
50 | Testing | Release | Rel-01: Bug Fixing | Fix bug P0/P1 truoc release. | 21/05 | 22/05
51 | Testing | Release | Rel-02: Deployment & Sanity | Deploy staging/prod va sanity check toan he thong. | 22/05 | 22/05